## Лист1
action | Estimated date | Real date | estimate time | realtime time
Collecting the information | 28jan-1feb | 1feb-4feb
Write down a TimeLog | 1 feb | 6 feb | 30 min | 30 min
Write down a Vision | 1 feb | 4 feb | 2 hours | 3 hours
Write down a Project plan | 3 feb | 5-6 feb | 3 hours | 4 hours
Write down Risk Analisys | 4 feb | 6 feb | 2 hours | 1hour 30min
Implement the basis of the game | 7 feb | 7 feb | 5 hours | 5 hours 30 min
Check and Correct everything | 8 feb | 8feb | 2hours | 3hours
Make a release | 8 feb | 8feb | 15 min | 15 min
TimeLog for Assignment 2 to on List 2

## Лист2
Activity | Estimated Time | Real Time
Study the book chapters 4-5 | 2 hours | 2.5 hours
Study the book chapters 6-7 | 2 hours | 1.5 hours
Create Use Case Model | 4 hours | 8 hours
Draw State Machine Diagram | 2 hours | 3 hours
Draw Class Diagram | 2 hours | 1 hour
Implement The Game / Refactor | 6 hours | 8 hours